## Marketing Plan Data
Marketing Plan Data
Marketing Plan Lists |  | Status Color Legend & Toggle
|  | Not Started | In Progress | Delayed | Complete | Custom 1 | Custom 2 | Custom 3 | Custom 4
|  | ON | ON | ON | ON | ON | ON | ON | ON
Task | Status | Owner | Assigned to | Anticipated Start Date | Anticipated End Date | Actual Start Date | Actual End Date | Estimated Cost | Actual Cost
Product Analysis | Not Started | John C. | John C. | 45108 | 45139 | 45105 |  | 1500 | 1250
Design Storyboards | In Progress | Mark M. | John C. | 45122 | 45153 | 45120 |  | 2000 | 1840
Review Storyboard Design | Delayed | Mark M. | John C. | 45139 | 45158 |  |  | 1450
Research Analysis Phase I | Complete | Kamil A. | Andrew L. | 45078 | 45108 | 45078 | 45105 | 3000 | 3200
Advertising Content Creation Phase I | Custom 1 | Kamil A. | Timothy S. | 45170 | 45184 |  |  | 500
Product Requirement Definitions | Custom 2 | Timothy S. | Vivian A. |  |  |  |  | 575 | 125
Prototype Development Specifications | Custom 3 | Kamil A. | Gabe F. | 45181 | 45194 |  |  | 1750
Quality Control, Progress Reports | Custom 4 | Mark M. | Kamil A. | 45108 | 45200 | 45108 |  | 925 | 250
Create Storyboards | Not Started | Mark M. | John C. | 45122 | 45153 | 45120 |  | 2000 | 1840
Review Storyboards with Graphic Artists | Delayed | Mark M. | John C. | 45139 | 45158 |  |  | 1450
Research Analysis Phase II | Complete | Kamil A. | Andrew L. | 45078 | 45108 | 45078 | 45105 | 3000 | 3200
Advertising Content Creation Phase II | Not Started | Kamil A. | Timothy S. | 45170 | 45184 |  |  | 500
Go to Marketing Plan Lists

## List Data
Marketing Plan Lists
Marketing Plan Data
Name | Title
John C. | Marketing Specialist
Mark M. | Marketing Manager
Kamil A. | Project Manager
Phil G. | Marketing Analyst
Andrew L. | Research Coordinator
Timothy S. | Marketing Specialist
Vivian A. | Marketing Analyst
Gabe F. | Associate Marketing Manager
Go to Marketing Plan Data