## Gantt Chart Template
|  |  |  | <COMPANY LOGO> | [10 empty] | Marketing Plan Gantt Chart Template
Name | Progress |  |  | Start* | Due* | Start on Day* | Duration* | User | Estimated Hours | Actual Hours | Estimated Cost | Actual Cost | Priority | Risk | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
Brainstorming session: | 85% | 0 | 4 | 2023-07-21 | 2023-07-25 |  |  |  | 25 | 28 | 100 |  | 5 | 4
Schedule tasks | 100% | 0 | 4 | 2023-07-21 | 2023-07-25 | 0 | 10 | John | 15 | 20 |  |  | 5 | 4
Assign content ideas | 70% | 3 | 6 | 2023-07-24 | 2023-07-27 | 3 | 4 | Alice | 10 | 8 |  |  | 5
Blog Design: | 100% | [7 empty] | 95 | 84 | 1600 | 1550 | 4 | 2
Define new look for blog | 100% | 4 | 8 | 2023-07-25 | 2023-07-29 | 4 | 5 | Mark | 2 | 2 |  |  | 4 | 2
Begin design process | 100% | 5 | 11 | 2023-07-26 | 2023-08-01 | 5 | 7 | Alice | 48 | 40 | 500 | 450 | 3 | 2
Define new CTAs | 100% | 10 | 12 | 2023-07-31 | 2023-08-02 | 10 | 3 | John | 45 | 42 | 300 | 325 | 2 | 1
Launch blog | 100% | 12 | 15 | 2023-08-02 | 2023-08-05 | 12 | 4 | Mike |  |  | 800 | 775 | 5 | 2
Scheduling: | 100% | [7 empty] | 112 | 98 | 350 | 250 | 4 | 3
Schedule new articles | 100% | 15 | 18 | 2023-08-05 | 2023-08-08 | 15 | 4 | Mark | 72 | 72 | 350 | 250 | 5 | 5
Publish new articles | 100% | 16 | 20 | 2023-08-06 | 2023-08-10 | 16 | 5 | Alice | 36 | 24 |  |  | 3 | 3
Assign new topics to writers | 100% | 20 | 24 | 2023-08-10 | 2023-08-14 | 20 | 5 | John | 4 | 2 |  |  | 5 | 1
Newsletter: | 95% | [7 empty] | 28 | 28 |  |  | 4
Choose topics | 100% | 23 | 33 | 2023-08-13 | 2023-08-23 | 23 | 11 | Mark | 5 | 4 |  |  | 5
Design layout | 100% | 23 | 33 | 2023-08-13 | 2023-08-23 | 23 | 11 | Wendy | 10 | 10 |  |  | 5
Write content | 100% | 24 | 34 | 2023-08-14 | 2023-08-24 | 24 | 11 | Alice | 10 | 12 |  |  | 5
Select publishing date | 100% | 25 | 34 | 2023-08-15 | 2023-08-24 | 25 | 10 | John | 1 | 0.5 |  |  | 2
Publish | 100% | 25 | 38 | 2023-08-15 | 2023-08-28 | 25 | 14 | Mark | 1 | 1 |  |  | 5
Share on Social Media | 70% | 26 | 38 | 2023-08-16 | 2023-08-28 | 26 | 13 | Mike | 1 | 0.5 |  |  | 3
Press Release: | 61.43% | [7 empty] | 53 | 50 | 855 | 655 | 4 | 3
Select media outlet | 100% | 30 | 38 | 2023-08-20 | 2023-08-28 | 30 | 9 | Mark | 10 | 9 |  | 150 | 5 | 3
Prepare content | 80% | 30 | 38 | 2023-08-20 | 2023-08-28 | 30 | 9 | John | 15 | 10 | 450 | 300 | 4 | 1
Prepare design | 50% | 30 | 38 | 2023-08-20 | 2023-08-28 | 30 | 9 | Alice | 20 | 24 | 100 | 100 | 3
Call media outlet | 100% | 33 | 39 | 2023-08-23 | 2023-08-29 | 33 | 7 | Alice | 1 | 1 | 100 | 50
Write press release | 100% | 33 | 39 | 2023-08-23 | 2023-08-29 | 33 | 7 | John | 5 | 4 | 105 | 105 | 5 | 4
Send to editor | 0% | 34 | 40 | 2023-08-24 | 2023-08-30 | 34 | 7 | Mike | 1 | 1
Send press release | 0% | 34 | 40 | 2023-08-24 | 2023-08-30 | 34 | 7 | Mark | 1 | 1
New web page: | 83.12% | [7 empty] | 9.5 | 9.5 | 100 | 150 | 4 | 3
Define look & feel | 100% | 36 | 42 | 2023-08-26 | 2023-09-01 | 36 | 7 | Alice | 3 | 3 | 100 | 150 | 4 | 3
Write sections | 100% | 37 | 42 | 2023-08-27 | 2023-09-01 | 37 | 6 | Wendy | 1 | 1
Approve sections | 100% | 38 | 42 | 2023-08-28 | 2023-09-01 | 38 | 5 | Mark | 1 | 1 |  |  | 4 | 4
UX/UI | 100% | 38 | 45 | 2023-08-28 | 2023-09-04 | 38 | 8 | John | 0.5 | 0.5 |  |  | 4 | 1
Write content | 100% | 40 | 46 | 2023-08-30 | 2023-09-05 | 40 | 7 | Wendy | 4 | 3 | 150 | 200 | 5 | 2
Approve design | 40% | 40 | 48 | 2023-08-30 | 2023-09-07 | 40 | 9 | Alice | 15 |  | 250 | 250 | 5 | 1
Share with team | 50% | 40 | 50 | 2023-08-30 | 2023-09-09 | 40 | 11 | Mark | 2
Launch new web | 75% | 40 | 50 | 2023-08-30 | 2023-09-09 | 48 | 2 | Jason | 1 |  |  |  | 5 | 1
Formulas:
Duration* = DATEDIF([Start*],[Due*],"d")+1

## Manual Chart Gantt Template
Marketing Plan Gantt Chart Template
Level | Name | Progress | Start | Due | User | Completion Date | Estimated Hours | Actual Hours | Estimated Cost | Actual Cost | Priority | Risk | Duration (Cal. Days) | 01/07/2019 | 01/08/2019 | 01/09/2019 | 01/10/2019 | 01/11/2019 | 01/12/2019 | 01/13/2019 | 01/14/2019 | 01/15/2019 | 01/16/2019 | 01/17/2019 | 01/18/2019 | 01/19/2019 | 01/20/2019 | 01/21/2019 | 01/22/2019 | 01/23/2019 | 01/24/2019 | 01/25/2019 | 01/26/2019 | 01/27/2019 | 01/28/2019 | 01/29/2019 | 01/30/2019 | 01/31/2019 | 02/01/2019 | 02/02/2019 | 02/03/2019 | 02/04/2019 | 02/05/2019 | 02/06/2019 | 02/07/2019 | 02/08/2019 | 02/09/2019 | 02/10/2019 | 02/11/2019 | 02/12/2019 | 02/13/2019 | 02/14/2019 | 02/15/2019 | 02/16/2019 | 02/17/2019 | 02/18/2019 | 02/19/2019 | 02/20/2019 | 02/21/2019 | 02/22/2019 | 02/23/2019 | 02/24/2019 | 02/25/2019 | 02/26/2019 | 02/27/2019 | 02/28/2019 | 03/01/2019 | 03/02/2019 | 03/03/2019 | 03/04/2019 | 03/05/2019 | 03/06/2019 | 03/07/2019 | 03/08/2019 | 03/09/2019 | 03/10/2019 | 03/11/2019 | 03/12/2019 | 03/13/2019 | 03/14/2019 | 03/15/2019 | 03/16/2019 | 03/17/2019 | 03/18/2019 | 03/19/2019 | 03/20/2019 | 03/21/2019 | 03/22/2019 | 03/23/2019 | 03/24/2019 | 03/25/2019 | 03/26/2019 | 03/27/2019 | 03/28/2019 | 03/29/2019 | 03/30/2019 | 03/31/2019 | 04/01/2019 | 04/02/2019 | 04/03/2019
1 | Brainstorming session: | 50% |  |  | Mark |  | 25 | 28 |  |  | 5 | 4 | 5
1 | Schedule tasks | 90% | 01/07/2019 | 01/11/2019 | John |  | 15 | 20 |  |  | 5 | 4 | 5
1 | Assign content ideas | 100% | 01/10/2019 | 01/11/2019 | Alice |  | 10 | 8 |  |  | 5 |  | 2
1 | Blog Design: | 100% |  |  |  |  | 95 | 84 | 1600 | 1550 | 4 | 2 | 12
1 | Define new look for blog | 100% | 01/14/2019 | 01/25/2019 | Mark |  | 2 | 2 |  |  | 4 | 2 | 12
1 | Begin design process | 100% | 01/15/2019 | 01/25/2019 | Alice |  | 48 | 40 | 500 | 450 | 3 | 2 | 11
1 | Define new CTAs | 100% | 01/21/2019 | 01/25/2019 | John |  | 45 | 42 | 300 | 325 | 2 | 1 | 5
1 | Launch blog | 100% | 01/25/2019 | 01/25/2019 | Mike |  |  |  | 800 | 775 | 5 | 2 | 1
1 | Scheduling: | 100% |  |  |  |  | 112 | 98 | 350 | 250 | 4 | 3 | 5
1 | Schedule new articles | 100% | 01/28/2019 | 02/01/2019 | Mark |  | 72 | 72 | 350 | 250 | 5 | 5 | 5
1 | Publish new articles | 100% | 01/30/2019 | 02/01/2019 | Alice |  | 36 | 24 |  |  | 3 | 3 | 3
1 | Assign new topics to writers | 100% | 02/01/2019 | 02/01/2019 | John |  | 4 | 2 |  |  | 5 | 1 | 1
1 | Newsletter: | 95% |  |  |  |  | 28 | 28 |  |  | 4 |  | 11
1 | Choose topics | 100% | 01/14/2019 | 01/18/2019 | Mark |  | 5 | 4 |  |  | 5 |  | 5
1 | Design layout | 100% | 01/16/2019 | 01/18/2019 | Wendy |  | 10 | 10 |  |  | 5 |  | 3
1 | Write content | 100% | 01/21/2019 | 01/23/2019 | Alice |  | 10 | 12 |  |  | 5 |  | 3
1 | Select publishing date | 100% | 01/21/2019 | 01/21/2019 | John |  | 1 | 0.5 |  |  | 2 |  | 1
1 | Publish | 100% | 01/24/2019 | 01/24/2019 | Mark |  | 1 | 1 |  |  | 5 |  | 1
1 | Share on Social Media | 70% | 01/24/2019 | 01/24/2019 | Mike |  | 1 | 0.5 |  |  | 3 |  | 1
1 | Press Release: | 61% |  |  |  |  | 53 | 50 | 855 | 655 | 4 | 3 | 15
1 | Select media outlet | 100% | 02/11/2019 | 02/12/2019 | Mark |  | 10 | 9 | 200 | 150 | 5 | 3 | 2
1 | Prepare content | 80% | 02/11/2019 | 02/15/2019 | John |  | 15 | 10 | 450 | 300 | 4 | 1 | 5
1 | Prepare design | 50% | 02/13/2019 | 02/15/2019 | Alice |  | 20 | 24 | 100 | 100 | 3 |  | 3
1 | Call media outlet | 100% | 02/18/2019 | 02/18/2019 | Alice |  | 1 | 1 |  |  |  |  | 1
1 | Write press release | 100% | 02/18/2019 | 02/21/2019 | John |  | 5 | 4 | 105 | 105 | 5 | 4 | 4
1 | Send to editor | 0% | 02/25/2019 | 02/25/2019 | Mike |  | 1 | 1 |  |  |  |  | 1
1 | Send press release | 0% | 02/25/2019 | 02/25/2019 | Mark |  | 1 | 1 |  |  |  |  | 1
1 | New web page: | 100% |  |  |  |  | 9.5 | 9.5 | 100 | 150 | 4 | 3 | 12
1 | Define look & feel | 100% | 02/18/2019 | 02/22/2019 | Alice |  | 3 | 3 | 100 | 150 | 4 | 3 | 5
1 | Write sections | 100% | 02/21/2019 | 02/21/2019 | Wendy |  | 1 | 1 |  |  |  |  | 1
1 | Approve sections | 100% | 02/21/2019 | 02/21/2019 | Mark |  | 1 | 1 |  |  | 4 | 4 | 1
1 | UX/UI | 100% | 02/26/2019 | 02/26/2019 | John |  | 1 | 1 |  |  |  |  | 1
1 | Write content | 100% | 02/20/2019 | 02/20/2019 | Wendy |  | 0.5 | 0.5 |  |  | 4 | 1 | 1
1 | Approve design | 100% | 03/01/2019 | 03/01/2019 | Alice |  | 3 | 3 |  |  |  |  | 1
1 | Share with team | 53% | 03/16/2019 | 03/16/2019 | Mark |  | 22 | 3 | 400 | 450 | 5 | 1 | 27
1 | Launch new web | 100% | 02/11/2019 | 02/22/2019 | Jason |  | 4 | 3 | 150 | 200 | 5 | 2 | 12
1 | New content | 40% | 02/18/2019 | 02/22/2019 | Victor Pascow |  | 15 |  | 250 | 250 | 5 | 1 | 5
1 | Choose topics | 50% | 02/22/2019 | 02/22/2019 | Wendy Torrance |  | 2 | [5 empty] | 1
1 | Design layout | 75% | 03/04/2019 | 03/04/2019 | Andy Barclay |  | 1 |  |  |  | 5 | 1 | 6
1 | Write content | 0% | 03/04/2019 | 03/04/2019 | Laurie Strode | [7 empty] | 1
1 | Select publishing date | 67% | 02/25/2019 | 03/11/2019 |  |  | 16 | 20 | 425 | 403 | 5 | 2 | 15
1 | Publish | 100% | 02/25/2019 | 02/27/2019 | Alice |  | 5 | 4 | 50 | 50 | 5 | 3 | 3
1 | Share on Social Media | 100% | 02/27/2019 | 03/05/2019 | Mark |  | 10 | 15 | 200 | 178 | 5 | 2 | 7
1 | Newsletter: | 100% | 03/04/2019 | 03/04/2019 | John |  | 1 | 1 |  |  | 4 | 1 | 1
1 | Choose topics | 100% | 02/28/2019 | 03/08/2019 | Wendy |  |  |  | 75 | 75 |  |  | 9
1 | Design layout | 0% | 03/11/2019 | 03/11/2019 | Jason |  |  |  | 100 | 100 | 4 | 1 | 1
1 | Write content | 0% | 03/11/2019 | 03/11/2019 | Mark | [7 empty] | 1
1 | Select publishing date | 49% |  |  |  |  | 120 |  | 600 |  | 4 | 3 | 24
1 | Publish | 100% | 03/11/2019 | 03/15/2019 | Alice |  | 72 |  |  |  | 5 | 1 | 5
1 | New brainstorming session: | 100% | 03/15/2019 | 03/15/2019 | Wendy |  | 1 | [5 empty] | 1
1 | Schedule session | 100% | 03/15/2019 | 03/15/2019 | Mark |  | 4 | [5 empty] | 1
1 | Write ideas | 40% | 03/18/2019 | 03/22/2019 | John |  | 25 |  | 300 |  | 5 | 4 | 5
1 | Assign content ideas | 50% | 03/19/2019 | 03/22/2019 | Wendy |  | 10 |  | 250 |  | 3 | 2 | 4
1 | Write content | 0% | 03/18/2019 | 03/22/2019 | Alice |  | 2 |  |  |  | 5 | 3 | 5
1 | Define dates | 0% | 03/26/2019 | 03/26/2019 | Mark |  | 1 |  |  |  | 3 |  | 1
1 | Review contents | 0% | 04/01/2019 | 04/03/2019 | Jason |  | 5 |  | 50 |  | 5 | 4 | 3