## Template
Shorts |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
Start Date: 04/01/2017 |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
DEVELOPMENT |  | 6 d
Finalize Script | L. Kasdan | 2 d | bar: WEEK 1 T to WEEK 1 W
Attachments | L. Wasserman | 3 d | bar: WEEK 1 TH to WEEK 1 SA
Financing | U. Moneybags | 6 d | bar: WEEK 1 M to WEEK 1 F; WEEK 2 M
PRE-PRODUCTION |  | 10 d
Casting | M.J. Slater | 3 d | bar: WEEK 1 TH to WEEK 1 SA
Set Design | B. Lider | 3 d | bar: WEEK 2 M to WEEK 2 W
Locations | G. Places | 2 d | bar: WEEK 2 T to WEEK 2 W
Costumes | H. Boss | 3 d | bar: WEEK 2 TH to WEEK 2 SA
Hair | V. Sassoon | 3 d | bar: WEEK 2 TH to WEEK 2 SA
Make-up | M. Factor | 3 d | bar: WEEK 2 TH to WEEK 2 SA
PRODUCTION |  | 7 d
Rehearsals | C. DeMille | 1 d | bar: WEEK 3 M
Principal Photography | C. DeMille | 5 d | bar: WEEK 3 T to WEEK 3 SA
Second Unit | S. Spielberg | 1 d | bar: WEEK 3 SU
POST-PRODUCTION |  | 8 d
Editing | Q. Tarantino | 7 d | bar: WEEK 3 SU to WEEK 4 SA
VFX | R. Harryhausen | 2 d | bar: WEEK 4 F to WEEK 4 SA
Scoring | J. Williams | 2 d | bar: WEEK 4 SA to WEEK 4 SU
Sound Editing | B. Osmo | 1 d | bar: WEEK 4 SU
Color Grading | M. Gervais | 1 d | bar: WEEK 4 SU
DISTRIBUTION
Distribution Deals | L. Wasserman
Marketing Push | L. Wasserman
Press Tour | E. Mannix
Premieres | E. Mannix
ANNOTATIONS |  |  | WEEK 4 TH: Blocked out event
Blocked out phase
[26 empty] | N | Dependency
[26 empty] | n | Dependent Event
#REF! |  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2017 - StudioBinder

## Month 1
Project Title... |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
Start Date: |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
DEVELOPMENT |  | 5 d
Finalize Script | owner | 2 d
Attachments | owner | 3 d
Financing | owner
PRE-PRODUCTION |  | x d
Casting | owner
Set Design | owner
Locations | owner
Costumes | owner
Hair | owner
Make-up | owner
PRODUCTION |  | x d
Rehearsals | owner
Principal Photography | owner
Second Unit | owner
POST-PRODUCTION |  | x d
Editing | owner
VFX | owner
Scoring | owner
Sound Editing | owner
Color Grading | owner
DISTRIBUTION |  | x d
Distribution Deals | owner
Marketing Push | owner
Press Tour | owner
Premieres | owner
ANNOTATIONS |  |  | WEEK 4 TH: Blocked out event
Blocked out phase
[26 empty] | N | Dependency
[26 empty] | n | Dependent Event
#REF! |  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2017 - StudioBinder