# Process for Requesting a LAB Contract Amendment

# * These instructions are for when the Materials Lab is the Principal investigator of a Research Contract.

# -Principal Investigator Instructions-

- Initiate the process to request a contract amendment as soon as you realize an amendment is needed, but no later than eight weeks prior to the contract expiration date. Examples of when an amendment is necessary include: time extensions, scope or work changes, task completion date alterations, budget revisions or transitions in principal or co-investigator(s).

- Work with the assigned Project Coordinator and Technical Liaison to discuss the necessary changes to the work plan as needed, (i.e. scope of work, time needed for each task, amount of money needed for tasks, etc.)

- Compose an Amendment request using the attached template. This template includes information required by MnDOT. A reason or justification must be provided.

- Prior to signing the Amendment Request, send it via email to the Project Coordinator and Technical Liaison to obtain their approval on the amendment request.

- After receiving approval from the Technical Liaison and Project Coordinator, mark the checkbox indicating this approval. Sign the Amendment Request and obtain signature from the Materials and Road Research department head.

- Send the approved Amendment Request Form via email to Debbie Sinclair, MnDOT Research Services & Library Financial Manager at debbie.sinclair@state.mn.us as an email attachment. If you have questions, you may reach her at 651-366-3746.

- Debbie Sinclair will review each Amendment request and obtain approval from Director of Research Services & Library section.

- A copy of the fully executed Amendment Request form will be emailed to the Principal Investigator, Technical Liaison and Project Coordinator.

- All amendment requested changes approved will be are in effect and updated to the Research Services & Library Automated Research Tracking System (ARTS) Database.

Click here to enter a date.

Debbie Sinclair

Financial Manager

Research Services & Library

Minnesota Department of Transportation

395 John Ireland Blvd., M.S. 330

St. Paul, MN  55155-1899

debbie.sinclair@state.mn.us

RE: 	Project Title: Click here to enter text.

Contract Number:  Click here to enter text.		    Work Order Number:  Click here to enter text.

Dear Ms. Sinclair:

Please consider my request for an amendment to the contract work order referenced above. Detailed information related to this request is as follows:

Please check all boxes that apply for this request. Add text for each box that you have checked. Refer to the current signed contract work order when filling out this request. Justification for requested changes must be provided explaining the need for the requested changes.

☐		Amendment for time extension OR change in task schedule.

NOTE: The minimum extension duration is six months for all time extension amendments.

- Requested revised end date (if applicable):  Click here to enter a date.

Provide a justification for reason the project could not be completed by original end date:

Click here to enter text.

- Project schedule amended as follows in the table below. NOTE: Include all tasks even if completed with any revised task begin and end dates.  Provide a justification for the schedule change:

Click here to enter text.

| Task | Current Task Start Date | Current End Date for Task Approval | Revised Task Start Date | Revised Due Date to Submit Draft Deliverables | Revised End Date for Task Approval |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |

- ☐	 Key Milestones

- ONLY if applicable (otherwise the Key Milestones will remain as stated in the original contract)

| Key Milestones | Target Date | Description |
| --- | --- | --- |

☐	Amendment for budget change (additional budget or re-budgeted costs).

Include a Revised detailed Budget for entire project along with a Revised Budget by Task, including any new tasks as appropriate, in the same format as in the approved WorkPlan.  Provide a justification Describe what changes are being made to the current budget, and why they are necessary:

Click here to enter text.

☐		Amendment for contract scope or work plan language change.

Please specify what section of the work plan will be amended, the scope or contract language change you are requesting, and what effect it has on the project schedule.  Provide a justification Describe what changes are being made to the current scope of work and why they are necessary:

Click here to enter text.

☐		Approval for change in Principal Investigator or Co-Investigator.

A work order amendment is not needed for a change in Principal Investigator or Co-Investigator. However, this letter should be used to document department head, Sponsored Project Administration, and MnDOT approval, as well as indicate that you have obtained TL and PC approval prior to requesting the change.

Name of New Principal Investigator:  Click here to enter text.

Name of New Co-Investigator:  Click here to enter text.

NOTE: Prior to signing the letter, send it via email to the Project Coordinator (PC) and Technical Liaison (TL) to obtain their approval on the amendment request. The PC will also forward the letter via email to the TL to request a timely approval.

☐	I have sent this form to the PC and TL (or Project Manager) and they approved this amendment request prior to obtaining signatures from the Department Head and SPA.

Thank you for your consideration of this request.

Sincerely,

| PI Name |  | Authorized Representative Name |
| --- | --- | --- |
| Principal Investigator |  | Manager, Materials and Road Research |

If requesting a change in PI or Co-Investigator:

New PI or Co-Investigator Name New PI or Co-Investigator

The amendment request outlined above is hereby approved.

| Authorized Representative Name Director, Research Services & Library Section Minnesota Department of Transportation |  | Date |
| --- | --- | --- |

Revised 02/13/2019

http://www.dot.state.mn.us/research/process-and-docs.html