Premium Solutions Company

Project

Management Plan

Prepared by

Thaddeus K. Hoffman

thaddeus@premiumsolcompany.com

March 27, 2030

Objectives

The main objectives of this project management plan are:

- Produce two short candid, homemade video clips captured on smartphones for social media content

- Increase the client's Instagram followers by 15% after posting the video campaigns

Strategy

The senior marketing researcher will create a creative flair for the video campaign development of the client’s new product. The senior marketing researcher will also consult with the client about the video and consult the lead marketing consultants if the project is going to be successful.

Team

Alexandra K. Lawson

Lead Marketing Consultant

She is assigned to lead the project for the client and to oversee the campaign.

Audrey G. Flynn

Senior Marketing Researcher

He is responsible for the creative video campaign outputs that will be posted on the social media accounts of the client.

Action Plan

OBJECTIVE 1

Produce two short candid, homemade video clips captured on smartphones for social media content

| ACTION | ASSIGNED TO | END DATE |
| --- | --- | --- |
| Draft a creative brief for each video | Alexandra K. Lawson | April 01, 2030 |
| Hold a meeting with the production team to discuss the video output | Alexandra K. Lawson | April 03, 2030 |

OBJECTIVE 2

Increase the client's followers on Instagram by 15% after posting the video campaigns

| ACTION | ASSIGNED TO | END DATE |
| --- | --- | --- |
| Analyze the client's social media footprint and determine the peak hours for posting new content | Audrey G. Flynn | April 05, 2030 |
| Research keywords and hashtags to include in captions to ensure each video content ranks high in search results | Audrey G. Flynn | April 07, 2030 |

Budget

| Description | Quantity | Price |  | Total |
| --- | --- | --- | --- | --- |
| Production Team | 1 | USD 25,000 | pkg | USD 25,000 |
| Materials | 1 | USD 1,500 | pkg | USD 1,500 |
| Total |  |  |  | USD 26,500 |