PLANNING AN EFFECTIVE

DIRECT MAIL CAMPAIGN

CHECKLIST

[YOUR COMPANY NAME]

Date:

People often underestimate what it takes to launch a successful direct mail campaign. A lot of tasks must be performed, and there is an order to follow. This checklist provides a step-by-step guide to make sure your message gets delivered to who you intend.

EIGHT WEEKS BEFORE MAIL DATE:

- Find the right lists of potential clients : Search through internal databases and contact list brokers

- Draft the message and find a creative idea to have a good impact on targeted prospects

- Outline the goals of the campaign

- Make a tempting offer and include a call to action

- Think about how you will measure the results of the direct mail campaign (like including rebate codes)

- Find a copywriter

- Find a graphic designer

- Get printing quotes

SIX WEEKS BEFORE MAIL DATE:

- Estimate postage costs

- Finalise your offering

- Obtain artwork

- Get customer testimonials for a copywriter

FOUR WEEKS BEFORE MAIL DATE:

- Sign deal with printers/sellers

- Set up key codes so that you know which list performs best

- Ensure that you have used the correct tone (personal but professional)

- Check addresses

- Verify spelling and Grammar

TWO WEEKS BEFORE MAIL DATE:

- Final list management: buy external lists and clean your own databases

- Check for errors

- Scan to see names, titles in the correct order

- Make sure each has a postal code

- Proofread all copy: consider this your final proof

- Finalise plans with fulfilment house or order takers

- Get all mailing permits (if needed)